TASKBOARD

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| User Story 1 - Validate Security Problems Sprint 1 |  | -Recruit and schedule interview participants across age groups - Conduct field interviews with households, businesses, and elderly residents - Develop interview guide and consent forms - Transcribe and code interview responses (pain level, willingness to pay) - Compile problem validation report summarising key insights |
| User Story 2 - Analyse Local Crime Data and Existing Security Measures Sprint 2 Sprint 2 |  | Gather secondary crime statistics data for the area - Map crime hotspots including load-shedding related spikes - Identify existing security measures (patrols, private security, police) - Document gaps in current security coverage - Present findings to team in Microsoft Teams |
| User Story 3 - Define Target User Personas Sprint 3 Sprint 3 |  | - Draft persona for household/family residents - Draft persona for small business and informal traders - Draft persona for elderly and vulnerable residents - Draft persona for community patrollers and guards -Validate personas against interview data |
| User Story 4 - Design Low-Fidelity Wireframes for Core App Screens Sprint 4 |  | - Sketch wireframe for onboarding/login screen - Sketch wireframe for incident reporting screen - Sketch wireframe for emergency alarm activation screen - Sketch wireframe for patrol tracking map screen - Sketch wireframe for subscription/payment screen. |
| User Story 5 - User Story 5: Design High-Fidelity UI Mockups Sprint 5 |  | - Create high-fidelity mockup for home dashboard - Create high-fidelity mockup for WhatsApp alert integration screen - Create high-fidelity mockup for guard/patrol profile screen - Create high-fidelity mockup for notifications screen - Apply SafeStreet brand colours, typography and iconography. |
| User Story 6 - Build Interactive Clickable Prototype Sprint 6 Sprint 6 |  | -Prepare prototype for usability testing session - Document prototype flow in a shared design file -Link wireframes into a clickable prototype flow - Add navigation between onboarding, reporting and alarm screens - Add micro-interactions for button states and alerts |

WALKTHROUGH

| - What do we need to do to advance this piece of work? | - Review the information collected from the community. - Use relevant information to improve the project documentation. - Review the proposed SafeStreet features and prototype. - Consider the feedback received from community members. |
| --- | --- |
| - Is anyone working on anything that is not on the board? | - Team members may be working on research, documentation or prototype-related tasks that need to be recorded on Trello. Any missing tasks should be discussed and added to the board. |
| - What do we need to finish as a team? | - Ensure the project documentation accurately reflects the research and proposed solution. - Review the Figma prototype and the proposed app features. - Record relevant feedback and identify possible improvements. |
| - Are there any bottlenecks or blockers to the flow of work? | - The team initially needed guidance on using Trello. - Some information collected during the research was not directly relevant to the project. - Team members needed to communicate and clarify information when they were unsure how to proceed. |

LOGBOOK

| Date: | 14 September 2026 |  |
| --- | --- | --- |
| Monday | - What did I complete since the last standup? | - Reviewed information relating to the community security problem SafeStreet was intended to address. - Organised relevant information for the project documentation. - Worked on documenting the proposed SafeStreet solution. - Communicated with team members when clarification was needed. |
|  | - What am I planning to complete between now and the next standup? | - Continue organising the information needed for the project documentation. - Check that the documented information relates to the community security problem. - Review the proposed app features with the team. |
|  | - What are my impediments (or risks or problems)? | - Some of the information collected initially appeared useful but was not directly relevant to the project. - I needed to ask team members questions when I was uncertain about information or how it should be used. |

| Date: | 15 September 2026 |  |
| --- | --- | --- |
| Tuesday | - What did I complete since the last standup? | - Continued reviewing information relevant to the SafeStreet project. - Organised project information to support the documentation. - Considered how the proposed solution and its features should be explained. - Communicated with team members to clarify information where necessary. |
|  | - What am I planning to complete between now and the next standup? | - Continue refining the project documentation. - Ensure the proposed solution is clearly explained. - Check that the documentation reflects the research and proposed app features. |
|  | - What are my impediments (or risks or problems)? | - Deciding which collected information was relevant required additional consideration. - Unclear information needed to be discussed with team members before it could be used. |

| Date: | 16 September 2026 |  |
| --- | --- | --- |
| Wednesday | - What did I complete since the last standup? | - Continued documenting the SafeStreet concept and its proposed features. - Reviewed the proposed user roles, including residents, guards and administrators. - Considered how the Figma prototype represented the proposed solution. - Contributed to organising the information needed to explain the project. |
|  | - What am I planning to complete between now and the next standup? | - Review the project documentation for clarity and consistency. - Check that the prototype and written explanation describe the same proposed solution. - Identify information that still needs clarification. |
|  | - What are my impediments (or risks or problems)? | - The proposed solution needed to be explained clearly because the prototype represented the design rather than a fully functional application. - Some information required further review before it could be included in the documentation. |

| Date: | 17 September 2026 |  |
| --- | --- | --- |
| Thursday | - What did I complete since the last standup? | - Reflected on the information collected and its relevance to SafeStreet. Reviewed the importance of communicating with team members when clarification was needed. - Considered how the research and community feedback informed the proposed solution. - Continued identifying areas where the project documentation could be improved. |
|  | - What am I planning to complete between now and the next standup? | - Continue refining the project documentation.Ensure the research, proposed features and prototype are explained consistently. - Record any outstanding work that needs to be discussed with the team. |
|  | - What are my impediments (or risks or problems)? | - Some collected information did not directly support the project objectives. - Ensuring that the documentation accurately reflected the work required careful review. |

| Date: | 18 September 2026 |  |
| --- | --- | --- |
| Friday | - What did I complete since the last standup? | - Reviewed the work completed on the SafeStreet project documentation - Reflected on my contribution as the Writer and Documentation team member. - Identified the importance of checking information before including it in project documents. Reflected on lessons learned about communication, asking questions and evaluating information. |
|  | - What am I planning to complete between now and the next standup? | - Continue improving my documentation and critical-thinking skills. - Apply the lessons learned when working on future project tasks. - Work with the team to clarify outstanding information and document further improvements. |
|  | - What are my impediments (or risks or problems)? | - Ensuring that all documentation accurately reflected the work completed required attention to detail. - Some information needed clarification before it could be used confidently. |